## Rebuild tracker
Site | Target domain | Trade | Screenshot | Assigned clone style | Photo inventory | Review inventory | Homepage build | CTA verification | Desktop QA | Mobile QA | Accessibility / SEO QA | Preview URL | Production URL | Release state | Notes
Connecticut Drain Pros | connecticutdrainpros.com | Drainage | Connecticut Drain PRos.jpeg | HorizonFix | 69 local target photos | Target reviews preserved | Rebuilt | Phone verified; server-side intake needed | Pass: 1440px | Pass: 390px | Pass: 0 errors; 3 image warnings | https://clone-rebuild.connecticut-drain-pros.pages.dev | https://connecticut-drain-pros.pages.dev | Preview deployed; production held | Horizon-style rebuild; noindex staging
Dallas Drain Guys | dallasdrainguys.com | Drainage | Dallas Drain Guys.jpeg | Minuteman | 32 local target photos | Target reviews preserved | Rebuilt | Phone verified; server-side intake needed | Pass: 1440px | Pass: 390px | Pass: 0 errors; 2 image warnings | https://clone-rebuild.dallas-drain-guys.pages.dev | https://dallas-drain-guys.pages.dev | Preview deployed; production held | Minuteman-style rebuild; noindex staging
Louisville Precision Walls | louisvilleprecisionwalls.com | Retaining walls | Louisville Precision Walls.jpeg | Pink's Concrete | 76 local target photos | Target reviews preserved | Rebuilt | Phone verified; server-side intake needed | Pass: 1440px | Pass: 390px | Pass: 0 errors; 8 image warnings | https://clone-rebuild.louisville-precision-walls.pages.dev | https://louisville-precision-walls.pages.dev | Preview deployed; production held | Pink's-style rebuild; noindex staging
Morgantown Fence Pros | morgantownfencepros.com | Fence | Morgantown Fence Pros.jpeg | Welborn Garage | 5 target remote photos | Target reviews preserved | Rebuilt | Phone verified; server-side intake needed | Pass: 1440px | Pass: 390px | Pass: 0 errors; 5 image warnings | https://clone-rebuild.morgantown-fence-pros.pages.dev | https://morgantown-fence-pros.pages.dev | Preview deployed; production held | Welborn-style rebuild; remote image availability needs QA
Pittsburgh French Drain | pghfrenchdrains.com | Drainage | Pittsburgh French Drain.jpeg | Roof Right Now | 45 local target photos | Target reviews preserved | Rebuilt | Phone verified; server-side intake needed | Pass: 1440px | Pass: 390px | Pass: 0 errors; 4 image warnings | https://clone-rebuild.pittsburgh-french-drain-site.pages.dev | https://pittsburgh-french-drain-site.pages.dev | Preview deployed; production held | Roof Right-style rebuild; noindex staging
Austin Drain Guys | austindrainguys.com | Drainage | Austin Drain Guys.jpeg | HorizonFix | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.austin-drain-guys.pages.dev |  | Preview deployed; production held | HorizonFix package adopted; brand, media, phone and reviews pending
Baltimore French Drain | baltimorefrenchdrain.com | Drainage | Blatimore French Drain.jpeg | Roof Right Now | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.baltimore-french-drain.pages.dev |  | Preview deployed; production held | Roof Right Now package adopted; screenshot filename retains source spelling
Charlotte Crawl Space | charlottecrawlspace.com | Crawlspace | Charlotte Crawl Space.jpeg | NextGen Windows | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.charlotte-crawl-space.pages.dev |  | Preview deployed; production held | NextGen Windows package adopted; final intake pending
Charlotte Precision Walls | charlotteprecisionwalls.com | Retaining walls | Charlotte Precision Walls.jpeg | Pink's Concrete | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.charlotte-precision-walls.pages.dev |  | Preview deployed; production held | Pink's Concrete package adopted; final intake pending
Chicago Drainage Guys | chicagodrainageguys.com | Drainage | Chicago Drainage Guys.jpeg | Minuteman | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.chicago-drainage-guys.pages.dev |  | Preview deployed; production held | Minuteman package adopted; final intake pending
Cincinnati Precision Walls | cincinnatiprecisionwalls.com | Retaining walls | Cincinnati Precision Walls.jpeg | Pink's Concrete | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.cincinnati-precision-walls.pages.dev |  | Preview deployed; production held | Pink's Concrete package adopted; final intake pending
Crawlspace Cary NC | crawlspacecarync.com | Crawlspace | Crawlspace Cary NC.jpeg | Trips Windows (small package) | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.crawlspace-cary-nc.pages.dev |  | Preview deployed; production held | Trips Windows small package adopted; final intake pending
Crawlspace Durham | crawlspacedurham.com | Crawlspace | Crawlspace Durham.jpeg | NextGen Windows | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.crawlspace-durham.pages.dev |  | Preview deployed; production held | NextGen Windows package adopted; final intake pending
Crawlspace Greensboro | crawlspacegreensboro.com | Crawlspace | Crawlspace Greensboro.jpeg | Welborn Garage | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.crawlspace-greensboro.pages.dev |  | Preview deployed; production held | Welborn Garage package adopted; final intake pending
Crawlspace Raleigh | crawlspaceraleigh.com | Crawlspace | Crawlspace Raleigh.jpeg | TripsWindows (full package) | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.crawlspace-raleigh.pages.dev |  | Preview deployed; production held | TripsWindows full package adopted; final intake pending
Crawlspace Wilmington | crawlspacewilmington.com | Crawlspace | Crawlspace Wilmington.jpeg | NextGen Windows | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.crawlspace-wilmington.pages.dev |  | Preview deployed; production held | NextGen Windows package adopted; final intake pending
Greensboro Drain Guys | greensborodrainguys.com | Drainage | Greensboro Drain Guys.jpeg | Roof Right Now | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.greensboro-drain-guys.pages.dev |  | Preview deployed; production held | Roof Right Now package adopted; final intake pending
Jackson French Drain | jacksonfrenchdrain.com | Drainage | Jackson French Drain.jpeg | HorizonFix | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.jackson-french-drain.pages.dev |  | Preview deployed; production held | HorizonFix package adopted; final intake pending
Little Rock French Drain | littlerockfrenchdrain.com | Drainage | Little Rock French Drain.jpeg | Roof Right Now | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.little-rock-french-drain.pages.dev |  | Preview deployed; production held | Roof Right Now package adopted; final intake pending
Little Rock Precision Walls | littlerockprecisionwalls.com | Retaining walls | Little Rock Precision Walls.jpeg | Pink's Concrete | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.little-rock-precision-walls.pages.dev |  | Preview deployed; production held | Pink's Concrete package adopted; final intake pending
Naples Pool Pros | naplespoolpros.com | Pool service | Naples Pool PRos.jpeg | Trips Windows (small package) | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.naples-pool-pros.pages.dev |  | Preview deployed; production held | Trips Windows small package adopted; final intake pending
Nashville Crawlspace | nashvillecrawlspace.com | Crawlspace | Nashville Crawlspace.jpeg | NextGen Windows | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.nashville-crawlspace.pages.dev |  | Preview deployed; production held | NextGen Windows package adopted; final intake pending
Nashville Backyards | nashvillebackyards.com | Backyard construction | Nashvlle Backyards.jpeg | Welborn Garage | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.nashville-backyards.pages.dev |  | Preview deployed; production held | Welborn Garage package adopted; screenshot filename retains source spelling
New Orleans French Drain | neworleansfrenchdrain.com | Drainage | New Orleans French Drain.jpeg | Roof Right Now | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.new-orleans-french-drain.pages.dev |  | Preview deployed; production held | Roof Right Now package adopted; final intake pending
PGH Painting Pros | pghpaintingpros.com | Painting | PGH Painting Pros.jpeg | Cincinnati Painting | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.pgh-painting-pros.pages.dev |  | Preview deployed; production held | Cincinnati Painting package adopted; final intake pending
PGH Pool Service | pghpoolservice.com | Pool service | PGH Pool Service.jpeg | TripsWindows (full package) | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.pgh-pool-service.pages.dev |  | Preview deployed; production held | TripsWindows full package adopted; final intake pending
Salt Lake City Precision Walls | saltlakecityprecisionwalls.com | Retaining walls | Salt Lake City Precision Walls.jpeg | Pink's Concrete | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.salt-lake-city-precision-walls.pages.dev |  | Preview deployed; production held | Pink's Concrete package adopted; final intake pending
Tulsa Drain Pros | tulsadrainpros.com | Drainage | Tulsa Drain PRos.jpeg | Minuteman | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.tulsa-drain-pros.pages.dev |  | Preview deployed; production held | Minuteman package adopted; final intake pending
WS Crawl Space | wscrawlspace.com | Crawlspace | WS Crawl Space.jpeg | Welborn Garage | 4 neutral placeholders; final media pending | Verified intake pending | Literal clone homepage adopted | Staging mailto; production intake pending | Pass: 1440x900 | Pass: 390x844; 320x780 | Pass: noindex; static audit | https://clone-rebuild.ws-crawl-space.pages.dev |  | Preview deployed; production held | Welborn Garage package adopted; final intake pending

## Overview
LLG Site Rebuild Tracker | Value
Captured sites | 29
First-wave rebuilds | 5
Remaining literal-clone rebuilds | 24
Preview deployments | 29
First-wave release state | Preview deployed; production held for verified intake
Publishing posture | Noindex Pages preview before production update
Credentials policy | Not copied into this workbook
Scope note | Custom domains, DNS, canonicals and public indexing require separate approval

## Style map
Clone style | Example assigned site | Style direction
HorizonFix | Connecticut Drain Pros | Full-bleed photographic hero, transparent navigation, cool-blue actions
Minuteman | Dallas Drain Guys | High-contrast navy/red service shell and direct conversion flow
Pink's Concrete | Louisville Precision Walls | Warm neutral canvas, rounded cards, orange-red action color
Welborn Garage | Morgantown Fence Pros | Bold energetic structure, yellow action color, strong proof modules
Roof Right Now | Pittsburgh French Drain | Saturated blue/white split hero with red estimate action
NextGen Windows | Charlotte Crawl Space | Dark geometric hero, top action strip and structured navigation
Cincinnati Painting | PGH Painting Pros | Charcoal geometric hero, oversized typography and red actions
Trips Windows (small) | Crawlspace Cary NC | Airy split hero, blue typography and rounded yellow actions
TripsWindows (full) | Crawlspace Raleigh | Expanded split hero and full source runtime package